## Project schedule
| Project 5 | [5 empty] | Project start: | [7 empty] | 2026-03-06
| Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken | [5 empty] | Display week: | [7 empty] | 1
[7 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-03-02 to 2026-04-26
 | time axis 2026-03-02 to 2026-04-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Project Preparation
| Project planning / review assignment requirements | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-03-05 | 2026-03-06 | 2
| Create Gantt Chart | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-03-05 | 2026-03-06 | 2
| Download and explore datasets (TGSIM CSV + Data Dictionary) | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-03-06 | 2026-03-08 | 3
| Initial dataset cleaning and inspection | Matthew Mendenhall, Gabreil Goeken |  | 2026-03-08 | 2026-03-10 | 3
| Identify key variables (position, velocity, acceleration, vehicle type) | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-03-10 | 2026-03-12 | 3
| Design flow diagram for analysis process |  |  | 2026-03-10 | 2026-03-13 | 4
| Create Flow Diagram submission | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-03-11 | 2026-03-13 | 3
| Write initial data processing code | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-03-12 | 2026-03-17 | 6
| Generate first trajectory visualizations | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-03-14 | 2026-03-19 | 6
| Develop behavioral analysis metrics | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-03-17 | 2026-03-20 | 4
| Prepare annotated code documentation | Kaleb Mangers |  | 2026-03-20 | 2026-03-25 | 6
| Draft reproducible methods section |  |  | 2026-03-20 | 2026-03-27 | 8
| Clean and finalize Python code | Matthew Mendenhall |  | 2026-03-26 | 2026-03-30 | 5
| Generate preliminary figures and tables | Matthew Mendenhall, Gabreil Goeken |  | 2026-03-31 | 2026-04-05 | 6
| Initial Results Submission | Matthew Mendenhall |  | 2026-03-31 | 2026-04-03 | 4
| Interpret early behavioral results | Gabriel Goeken |  | 2026-04-06 | 2026-04-10 | 5
| Refine analysis and improve visualizations | Gabriel Goeken |  | 2026-04-06 | 2026-04-10 | 5
| Write discussion of AV vs non-AV behavior |  |  | 2026-04-06 | 2026-04-12 | 7
| Compile full analysis notebook and files | Matthew Mendenhall, Kaleb Mangers, Gabriel Goeken |  | 2026-04-13 | 2026-04-16 | 4
| Prepare files for peer review | Kaleb Mangers |  | 2026-04-15 | 2026-04-17 | 3
| Peer Review Submission | Matthew Mendenhal |  | 2026-04-15 | 2026-04-17 | 3
| (Nothing shown as due this week) |  |  | 2026-04-18 | 2026-04-21 | 4
|  |  |  | 2026-04-20 | 2026-04-25 | 6
Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.